## Sheet1
|  |  |  | BARE PLANES |  | LLC
|  |  |  | STATUS SHEET |  |  |  | DUE NOW
N72TG |  |  |  | BEECH C90A |  |  |  | DUE AT OR BEFORE
LJ-1252 | AC HOUR | [6 empty] | NEXT INSPECTION
D.O.M. 6-25-90 | 33.7 |  |  |  | LEFT | RIGHT |  | OVER DUE
|  |  |  | P&WC PT6A-135A | PCE-PZ0419 | PCE-PZ0421 |  | ITEMS TO BE NOTED
|  |  |  | ETSN | 3371.4 | 3371.4 |  | ALL ENGINE TIMES
HOURMETER | 3188 |  |  | TSOH | NA | NA |  | ARE TTSN (ETSN)
ADJUSTMENT | 5522.8 |  |  | TSHSI | 1045.4 | 955.4
TOTAL TIME | 8710.8 |  |  | CSN | 2485 | 2485 |  | ALL AIRCRAFT TIMES
DATE | 2024-01-15 |  |  | HART HC-D4N-3C | FY-2938 | FY-2942 |  | ARE TTSN (ACTT)
CYCLES | 7700 |  |  | PTSN | 3371.4 | 3371.4
TIME ELAPSED |  |  |  | TSOH | 428.3 | 428.3 |  | ALL CYCLES PER PILOT
ITEM | TYPE | C/W | INC | INTERVAL | DUE | REMAIN |  | REMARKS
PHASE 1 | INSP | 8587.3 | 800 | 800 HR | 8987.3 | 276.5 | HR
PHASE 2 | INSP | 8587.3 | 800 | 800 HR | 8987.3 | 276.5 | HR
PHASE 3 | INSP | 8391 | 800 | 800 HR | 8787.3 | 76.5 | HR
PHASE 4 | INSP | 8391 | 800 | 800 HR | 8787.3 | 76.5 | HR
PHASES 1 THRU 4: | INSP | 2022-05-15 | 730 | 24 MO | 2024-05-14 | 3.9474 | MO | DUE EACH 24 MO
LAST CYCLE COMPLETED |  | 8391 | 800 | 800 HR | 9191 | 480.2 | HR
AD 2002-01-10, TORQUE KNEES | INSP | 7579 | 1000 | 1000 CYC | 8579 | 879 | CY
AFT PRESS BKHD & FUSELAGE | INSP | 0 |  | 9000 CYC | 9000 | 1300 | CY | SEE CH. 53-10-00
AILERON DETAILED | INSP | 8206 |  | 800 HR | 9006 | 295.2 | HR
AIRCOND, MOTOR BRUSHES | INSP | 2844 |  | 500 HR | 3344 | 3310.3 | HR
AIRSTAIR DOOR & FUS. FRAME | INSP | 0 |  | 9000 CYC | 9000 | 1300 | CY | SEE CH. 53-10-00
AIRSTAIR LATCH BOLTS | REPLACE | 5147 | 5000 | 5000 CYC | 10147 | 2447 | CY | DUE EACH 5K
AIRSTAIR UPER HOOKS | REPLACE | 0 | 10000 | 10000 CYC | 10000 | 2300 | CY | DUE EACH 10K
#1 ALTIMETER | CERTIFY | 2023-03-10 | 730 | 24 MO | 2025-03-09 | 13.7829 | MO
#2 ALTIMETER | CERTIFY | 2023-03-10 | 730 | 24 MO | 2025-03-09 | 13.7829 | MO
#1 TRANSPONDER | CERTIFY | 2023-03-10 | 730 | 24 MO | 2025-03-09 | 13.7829 | MO
#2 TRANSPONDER | CERTIFY | 2023-03-10 | 730 | 24 MO | 2025-03-09 | 13.7829 | MO
BATTERY, LEAD ACID | 1ST CAP CK | 8587.3 |  | 800 HR | DONE | DONE | HR | GILL STC INSTALLED
|  | 2023-03-10 |  | 12 MO | DONE | DONE | MO | VRSLA P/N G-6381E
BATTERY, LEAD ACID | REC CAP CK | 8587.3 | 200 | 200 HR | 8787.3 | 76.5 | HR | SEE MFG ICA
Recurring Cap Check |  | 2023-03-10 | 365 | 6 M0 | 2024-03-09 | 1.7763 | MO
CABIN ALTITUDE WARNING SYS. | TEST | 2023-03-10 |  | 12 MO | 2024-03-09 | 1.7763 | MO
CVR---ULB | TEST | NA | 730 | 24 MO | #VALUE! | #VALUE! | MO | EQUIPMENT NOT INSTALLED
CVR---ULB BATTERY | REPLACE | NA |  | AS DATED | #VALUE! | #VALUE! | MO | EQUIPMENT NOT INSTALLED
EDGE LIGHTED PANEL | INSP | 8206 | 2000 | 2000 HR | 10206 | 1495.2 | HR
|  | 2020-10-15 | 1460 | 4 YR | 2024-10-14 | 8.9803 | MO
ELT FAR 91.207(d) | INSP/TEST | 2023-03-10 | 365 | 12 MO | 2024-03-09 | 1.7763 | MO | ME 406
ELT BATTERY | REPLACE | 2021-05-15 |  | AS DATED | 2029-06-15 | 65.0658 | MO
EVAPORATOR FILTER | REPLACE | 8587.3 |  | 400 HR | 8987.3 | 276.5 | HR | 90-555101-0001
EXTERIOR SKIN | INSP | 0 | 10000 | 10000 CYC | 10000 | 2300 | CY | 10K INIT THEN 1K
FIRE EXTINGUISHER, CABIN | HYDRO | 2020-01-15 | 4380 | 12 YR | 2032-01-12 | 96.0197 | MO
FIRE EXTINGUISHER, COCKPIT | HYDRO | 2020-01-15 | 4380 | 12 YR | 2032-01-12 | 96.0197 | MO
FLAP FLEX SHAFT | INSP | 5147 | 5000 | 5000 CYC | 10147 | 2447 | CY | LJ527-UP & LW1-UP
FLIGHT CONTROLS | INSP | 0 | 10000 | 10000 CYC | 10000 | 2300 | CY | 10K INIT THEN 5K
FUEL PROBE | CLEAN & | 8587.3 | 2400 | 2400 HR | 10987.3 | 2276.5 | HR
| INSP | 2023-05-10 | 930 | 30 MO | 2025-11-25 | 22.3684 | MO
FUSELAGE INSPECTION | INSP | 6144 | 9000 | 6000 CYC | DONE | DONE | CY | 6K INITIAL, 3K RECURRING
|  | 6144 |  | 3000 CYC | 9144 | 1444 | CY | INITIAL C/W TAS 6-2010
INSTRUMENT AIR FILTER | REPLACE | 8391 |  | 800 HR | 9191 | 480.2 | HR
ITEM | TYPE | C/W |  | INTERVAL | DUE | REMAIN |  | REMARKS
LANDING GEAR BRAKE HOSES | REPLACE | 2020-07-15 |  | 5 YR | 2025-07-14 | 17.9605 | MO
LANDING GEAR, CLEVIS (3EA) | INSP | 7579 | 1000 | 1000 CYC | 8579 | 879 | CY
LUBE SCHEDULE, 200 HR | LUBE | 8587.3 |  | 200 HR | 8787.3 | 76.5 | HR
LUBE SCHEDULE, 400 HR | LUBE | 8587.3 |  | 400 HR | 8987.3 | 276.5 | HR
LUBE SCHEDULE, 800 HR | LUBE | 8187 |  | 800 HR | 8987 | 276.2 | HR
LUBE SCHEDULE, 1200 HR | LUBE | 8587.3 |  | 1200 HR | 9787.3 | 1076.5 | HR
HYDRAULIC LANDING GEAR | INSP | 7579 | 8000 | 8000 CYC | 15579 | 7879 | CY
ASSEMBLY (3EA) |  | 2020-07-15 | 2190 | 6 YR | 2026-07-14 | 29.9671 | MO
LANDING GEAR, HYD SYS FILTER | CLEAN/INSP | 8282 | 1200 | 1200 HR | 9482 | 771.2 | HR
|  | 7646 |  | 1000 CYC | 8646 | 946 | CY
LANDING GEAR, EMER PUMP FILTER | CLEAN/INSP | 8282 |  | 800 HR | 9082 | 371.2 | HR
LANDING GEAR, EXT/RET HOSES | REPLACE | 2022-04-15 | 3648 | 10 YR | 2032-04-10 | 98.9474 | MO
MECHANICAL LANDING GEAR | INSP | NA | 8000 | 8000 CYC | #VALUE! | #VALUE! | CY
ASSEMBLY (3EA) |  | NA | 2190 | 6 YR | #VALUE! | #VALUE! | MO
LANDING GEAR, ACTUATOR | INSP | NA | 8000 | 8000 CYC | #VALUE! | #VALUE! | CY
(3EA) |  | NA | 2190 | 6 YR | #VALUE! | #VALUE! | MO
ACTUATOR, END PLAY CHECK | INSP | NA | 1000 | 1000 CYC | #VALUE! | #VALUE! | CY
(3EA) |  | NA | 912 | 30 MO | #VALUE! | #VALUE! | MO
MOTOR, GEARBOX, & CLUTCH | OVERHAUL | NA | 8000 | 8000 CYC | #VALUE! | #VALUE! | CY
|  | NA | 2190 | 6 YR | #VALUE! | #VALUE! | MO
NACELLE SPLICE PLATES | INSP | 0 |  | 10,000 HR | 10000 | 1289.2 | HR
| REPLACE | 0 |  | 20,000 HR | 20000 | 11289.2 | HR
OXYGEN BOTTLE, 3HT 1850 (LT. WT.) | HYDRO | 2021-06-15 | 1095 | 3 YR | 2024-06-14 | 4.9671 | MO
| REPLACE | 2008-09-15 | 8820 | 24 YR | 2032-11-08 | 105.9211 | MO
OXYGEN REGULATOR | OVERHAUL | 2021-06-15 | 1825 | 3 YR | 2024-06-14 | 4.9671 | MO
POWER LEVER STOP PIN | INSP | 8587.3 | 1200 | 1200 HR | 9787.3 | 1076.5 | HR
PNUEMATIC FLOW PACK FILTER | CLEAN | 8587.3 |  | 800 HR | 9387.3 | 676.5 | HR
PRESSURIZATION CONTROL FILTER | REPLACE | 8587.3 |  | 800 HR | 9387.3 | 676.5 | HR | P/N 146898-1
RUDDER BOOST FILTER | REPLACE | 8587.3 |  | 800 HR | 9387.3 | 676.5 | HR | 2J4-7
SPAR CAP | INSP | 2023-03-10 | 365 | 12 MO | 2024-03-09 | 1.7763 | MO | 5 YR INIT THEN 1 YR
VACUUM REGULATOR FILTER | REPLACE | 8587.3 |  | 400 HR | 8987.3 | 276.5 | HR
WING BOLT | REPLACE | 2005-08-15 | 5475 | 20 YR | 2025-08-10 | 18.8487 | MO
WING BOLT | INSP | 2020-10-15 |  | 5 YR | 2025-10-14 | 20.9868 | MO
STRUCTURAL INSPECTION (NDT) | S.I.R.M. | 8206 |  | 5000 HR | 13206 | 4495.2 | HR | S.I.R.M. CH. 53
WINDSHIELD ATTACH SCREWS, LH | REPLACE | 0 |  | 10000 CYC | 10000 | 2300 | CY | DUE EACH 10000 CYC
WINDSHIELD ATTACH SCREWS, RH | REPLACE | 0 | 10000 | 10000 CYC | 10000 | 2300 | CY | DUE EACH 10000 CYC
LEFT ENGINE | OVERHAUL | 0 | 3600 | 3600 HR | 3600 | 228.6 | HR | SEE P&W SB 1003
HOT SECTION | INSP | 2326.4 | 1800 | 1800 HR | 4126.4 | 755 | HR | SEE P&W SB 1003
STARTER GENERATOR | OVERHAUL | 8206 | 1000 | 1000 HR | 9206 | 495.2 | HR
OIL FILTER | REPLACE | 8587.3 | 1000 | 1000 Hr | 9587.3 | 876.5 | HR
P3 FILTER | REPLACE | 8587.3 |  | 1000 HR | 9587.3 | 876.5 | HR
FLAMMABLE FLUID HOSES | REPLACE | 2017-05-15 | 1825 | 10 YR | 2027-05-13 | 39.9342 | MO
ENGINE MOUNTS | REPLACE | 7489 | 4000 | 4000 HR | 11489 | 2778.2 | HR
|  | 7489 | 3600 | 3600 HR | 11089 | 2378.2 | HR | OR 4000 HR
PROPELLER | OVERHAUL | 8282 | 3000 | 4000 HR | 12282 | 8910.6 | HR
HC MAN. 149 61-00-49 pg 5-7 Rv 8 Nov 99 |  | 2021-06-15 | 1825 | 6 YR | 2027-06-14 | 40.9868 | MO
OVERSPEED GOVERNOR | OVERHAUL | 3560.6 | 6500 | 6500 HR | 10060.6 | 1349.8 | HR | SEE SB 33580 L
|  | NA | 2190 | 6 YR | #VALUE! | #VALUE! | MO
PRIMARY GOVERNOR | OVERHAUL | 0 | 4500 | 4500 HR | 4500 | 1128.6 | HR | SEE SB 33580 L
|  | NA | 2190 | 6 Yr | #VALUE! | #VALUE! | MO
FUEL NOZZLES | CLEAN/TEST | 8391 | 400 | 400 HR | 8791 | 80.2 | HR
BOROSCOPE | INSP | 8391 |  | 400 HR | 8791 | 80.2 | HR
RIGHT ENGINE | OVERHAUL | 0 | 3600 | 3600 HR | 3600 | 228.6 | HR
HOT SECTION |  | 2416 | 1800 | 1800 HR | 4216 | 844.6 | HR
STARTER GENERATOR | OVERHAUL | 8206 | 1000 | 1000 HR | 9206 | 495.2 | HR
OIL FILTER | REPLACE | 8587.3 | 1000 | 1000 HR | 9587.3 | 876.5 | HR
P3 FILTER | REPLACE | 8587.3 |  | 1000 HR | 9587.3 | 876.5 | HR
FLAMMABLE FLUID HOSES | REPLACE | 2017-05-15 | 1825 | 10 YR | 2027-05-13 | 39.9342 | MO
ENGINE MOUNTS | REPLACE | 7489 | 4000 | 4000 HR | 11489 | 2778.2 | HR
|  | 7489 | 3600 | 3600 Hr | 11089 | 2378.2 | HR | DUE AT ENG O/H
PROPELLER | OVERHAUL | 8282 | 3000 | 4000 HR | 12282 | 8910.6 | HR
HC MAN. 149 61-00-49 pg 5-7 Rv 8 Nov 99 |  | 2021-06-15 | 1825 | 6 YR | 2027-06-14 | 40.9868 | MO
OVERSPEED GOVERNOR | OVERHAUL | 3596.6 | 6500 | 6500 HR | 10096.6 | 1385.8 | HR | SEE SB 33580 L
|  | NA | 2190 | 6 YR | #VALUE! | #VALUE! | MO
PRIMARY GOVERNOR | OVERHAUL | 0 | 4500 | 4500 HR | 4500 | 1128.6 | HR | SEESB 33580 L
|  | NA | 2190 | 6 YR | #VALUE! | #VALUE! | MO
FUEL NOZZLES | CLEAN/TEST | 8391 | 400 | 400 HR | 8791 | 80.2 | HR
BOROSCOPE | INSP | 8391 |  | 400 HR | 8791 | 80.2 | HR
NOTES:
WOODWARD CALENDAR TIMES ONLY APPLY TO A/C OPERATED UNDED 10HR/MO | [5 empty] | WOODWARD | SB | 33580L
STRATUS ESG INSTALLED 8/19 | ADSB COMPLIANT
KAD AERO LED STROBE LIGHT STC SA03902NY INSTALLED 8/19 BY FLYTEX
CLEVELAND NLG WHEEL STC SA1077GL INSTALLED 3-11 BY STEVENS BRM | [6 empty] | STC | KIT 199-126 RK
ME406 ELT INSTALLED 11-08 | [6 empty] | PMA | P/N 455-6607 S/N 13530
P&I BY LEGACY, YUKON, 12-08 | 570-505 WH | 10568 SILV |  | 1955 BLK | 550 RED |  | CRS | L50R364Y
FRAKES EXHAUST STC SA6710SW INSTALLED 12-06 BY STEVENS BRM | [6 empty] | STC
CENTEX STC SA1033956 INSTALLED 12-06 BY STEVENS BRM | [6 empty] | STC
RAISBECK STC SA3593NM INSTALLED 12-06 BY STEVENS BRM | [6 empty] | STC | HC-D4N-3C
BLACKHAWK STC SA10341SC INSTALLED 12-06 BY STEVENS BRM | [6 empty] | STC | PT6A-135A
RAISBECK SB 08-BC-01, DATED JAN-04, INSTALLED | [6 empty] | SB | GROSS WT INCR 10,500 LB
R134A SYSTEM CONVERSION BEECH COMM. 2006-1 JUN-06 BY TULSAIR | [5 empty] | SANDEN | KIT | P/N 90-5077-1
MAINTENANCE EVENTS:
O/H'D PILOT WDSHD INSTALLED 12-04 BY CUTTER ABQ 4709 CYC
NEW AC COMPRESSOR INSTALLED 3-11 BY STEVENS BRM
NEW AC DRIVE MOTOR INSTALLED 9-18 BY FLYTEX | [5 empty] | 2362hm |  | ***500hr brush replace due ??***
ENGINE HOSE KIT, 5 YEAR REPLACE | [7 empty] | PRECISION HOSE TECH, TULSA
130F003-12D0414 | L&R SAME | [5 empty] | 2X | OIL COOLER
130F006G0100D180 | L&R SAME | [5 empty] | 2X | OIL COOLER
130F002-10D0145 | L&R SAME | [5 empty] | 2X | FUEL HEATER TO COUNTER
130F002-4S0180 | LH ONLY |  |  |  |  | LH ENGINE | 1X | F/W TO FUEL CONTROL
130F002-4S0090 | RH ONLY |  |  |  |  | RH ENGINE | 1X | F/W TO FUEL CONTROL
130F001-4S0104 | L&R SAME | [5 empty] | 2X | TORQUE PRESS TRANSMITTER
130F001-4S0314 | L&R SAME | [5 empty] | 2X | TORQUE PRESSURE
111417-4S0140 | L&R SAME | [5 empty] | 2X | PROP SEAL DRAIN
13002-4S0204 | L&R SAME | [5 empty] | 2X | FORWARD DRAIN
13001-4S0140 | L&R SAME | [5 empty] | 2X | FORWARD DRAIN
13002-6S0114 | L&R SAME | [5 empty] | 2X | FORWARD DRAIN
THIS FORM IS TO BE USED AS REFERENCE ONLY.
FAA AIRCRAFT AND ENGINE MAINTENANCE RECORDS ARE LEGAL DOCUMENTATION
Formulas:
LEFT = [C/W]+[INC]
LEFT = SUM([C/W]+[INC])